## Template
Project Name | SAP ID | Site | Date Reported | Process Area | Goal | Practice | Finding | Rating | Category

## July Data
Project Name | SAP ID | Site | Date Reported | Process Area | Goal | Practice | Finding | Rating | Category
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | PP | 1 | 1.1 | No evidence of internal (IGT) and external (customer) project scope approval | LI
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | IPM | 1 | 1.1 | • Project practices do not fully reflect Waterfall SDLC requirements per project plan • No evidence of approved tailoring to account for deviations | LI
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | PMC | 1 | 1.7 | No evidence project conducted the milestone reviews listed below for BTC 1 and 2 o Initial/Beginning of Development o Release to Integration o Release to Production o Go-live | LI
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | VER | 2 | 2.3 | • Code review results for the ESTE critical code were not submitted to the PRMS • No evidence of SRS peer review results in the PRMS | LI
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | REQM | 1 | 1.3 | No evidence customer approved of Go-Live date changes | LI
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | REQM | 1 | 1.3 | No evidence customer approved of scope changes | LI
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | TS | 3 | 3.1 | Release Notes for ESRS, ESTE, and ES IPS Host are missing information | LI
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | TS | 3 | 3.1 | No evidence RNs were approved by the Director of Operations/Quality Assurance in accordance with Section 12 Gtech Approvals | LI
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | SAM | Obv | Obv | Project should incorporate IDM and CMMI SAM requirements when interacting with 3rd party vendors. | Obv
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | PP | Obv | Obv | Program should consider establishing a program level software development plan to manage batch planning instead of establishing a plan for each batch. | Obv
CY1604 ES Anywhere Batch | NY23598 | New York | 2016-07-08 | IPM | Obv | Obv | No evidence project tailored process to account for alternative processes | Obv
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PP | SG1 | 2.7 | No evidence of SDP. | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PP | SG1 | 2.7 | No evidence of Training Plan. (OT) Not an issue
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PP | SG1 | 2.7 | No evidence of CMP approved. (CM) Late CMP Work Product Approval. | LI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PP | SG1 | 1.1 | No evidence of PSS approved by ADM, RL and Customer. | LI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PP | SG1 | 3.3 | No evidence of Kickoff Meeting. | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PP | SG1 | 2.2 | Unable to verify CCB team defined. (CM) | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | IPM | SG1 | 1.1 | OBSERVATION: The project should consider Tailoring Request for using different location for project documentation than Clarity and the use of different templates, meeting minutes and SSDs. | OBV
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | IPM | SG1 | 1.4 | Critical Path in Milestone has not identified. Late Milestones indicated in Clarity schedule | LI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | IPM | SG1 | 1.4 | Unable to verify Lesson Learned Mtg. The project went live on 05-Jun; however LL Mtg is not scheduled yet. Unable to verify Lesson Learned Mtg completed. Project Schedule, DRE, RL score, Review project deliverables sections are missing. | LI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PMC | SG1 | 1.2 | No evidence of all required sections included in Mtg Minutes. No evidence of Meeting agenda template used. | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PMC | SG1 | 1.4 | Unable to verify the status of planned project documentation (SDP, CMP, SDD, etc) monitored during weekly meetings. | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PMC | SG1 | 1.7 | No evidence of Development, Integration, System Test and CAT Milestone Reviews. | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PMC | SG1 | 1.7 | No evidence of Go Live Meeting. | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PMC | SG1 | 2.2 | No evidence of Change Request closed out however the project went live. (CM) | LI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | RSKM | SG1 | 2.1 | OBSERVATION: No risks logged for the project at all. | OBV
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | REQM | SG1 | 1.4 | Unable to verify the project managing traceability of requirements by using MPI tool. | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | REQM | SG1 | 1.3 | Unable to verify CRs monitored during weekly meetings and milestones. | LI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | REQM | SG1 | 1.5 | Unable to verify Change Requests for requirements; however SRS has been updated several times (revision 1.0 - 1.7). | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | RD | SG1 | 1.2 | No evidence of SRS approved by PM, PgM, ADM and Customer. There is no decision posted nor Risk opened to internal approve. | LI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | RD | SG1 | 1.1 | Unable to verify CZH CY16 GSM project is using DOORS and MPI as Summary MPI report is blank. | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | TS | SG1 | 2.1 | No evidence of project used the current template for SDDs. | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | TS | SG1 | 2.1 | Unable to verify Critical Code section completed for SDD Terminal/OLTP. | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | TS | SG1 | 2.1 | No evidence of SDD GWARE Host, GWARE PC, OLPM and LSH. | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | TS | SG1 | 2.1 | Unable to verify SDDs approved. | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | TS | SG1 | 2.1 | Unable to verify Critical Computer Resources completed in SDDs GWARE Host, GWARE PC, Terminal, OLPM and LSH. | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | TS | SG1 | 3.1 | No evidence of Unit Test Description completed for Software Design Descriptions (SDDs). | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | TS | SG1 | 3.1 | No evidence of Unit Test results completed for Release Notes (RNs). | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | TS | SG1 | 3.1 | Unable to verify Release Notes (RNs) were approved. | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | TS | SG1 | 3.1 | No evidence of Release Notes (RNs) for Terminal, OLPM and LSH. | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PI | SG1 | 1.1 | Unable to verify Integration Test results logged. No evidence of “LOG” tab filled out. | PI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PI | SG1 | 1.3 | No evidence of CAT and Production Product Release Request (CM). | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | PI | SG1 | 3.4 | No evidence of Installation Procedure. Late Installation Procedure work product; however not approved. | LI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | VER | SG1 | 2.1 | No evidence of the approval for QA Test Plan (VAL) | LI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | VER | SG1 | 2.1 | No evidence of QA Test Procedures. (VAL) | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | VER | SG1 | 2.1 | Unable to verify Weekly Test Summary Reports as referenced in QA Test Plan. (VAL) Not an issue
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | VER | SG1 | 2.1 | No evidence of the final Summary Test Report. | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | VER | SG1 | 2.1 | The project did not conduct any peer reviews for any work products. | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | VAL | SG1 | 2.2 | Unable to verify the project satisfies the readiness criteria to proceed to CAT. | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | VAL | SG1 | 2.1 | No evidence of the final Summary Site Test and CAT Report. | NI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | CM | SG1 | 3.1 | Unable to verify the project reports the status of Configuration Items during weekly meetings. | LI
CZH CY16 GSM eTopup Vouchers | CZH23242 | Czech | 2016-07-27 | CM | SG1 | 3.1 | No evidence of Configuration management for the project work products and software deliverables | NI
IN CY15 Hoosier Lotto/New Game | IN22810 | Indiana | 2016-06-02 | CM | 1 | 1.1 | No evidence of Development, Integration, SQA baseline | NI
IN CY15 Hoosier Lotto/New Game | IN22810 | Indiana | 2016-06-02 | TS | 3 | 3.1 | No evidence of all RNs in Clarity. Release notes were included in Jira. | PI
IN CY15 Hoosier Lotto/New Game | IN22810 | Indiana | 2016-06-02 | CM | 1 | 1.3 | No evidence of CAT and Production PRR | PI
IN CY15 Hoosier Lotto/New Game | IN22810 | Indiana | 2016-06-02 | PMC | 1 | 1.2 | Weekly meetings and Kickoff mtg not documented | NI
IN CY15 Hoosier Lotto/New Game | IN22810 | Indiana | 2016-06-02 | PMC | 1 | 1.7 | No evidence of Development, Integration, SQA, CAT milestone readiness | NI
IN CY15 Hoosier Lotto/New Game | IN22810 | Indiana | 2016-06-02 | PP | 2 | 2.7 | • No evidence of SPP • No evidence of PSS • No evidence of Full PAF • No evidence of Project Estimates | NI
IN CY15 Hoosier Lotto/New Game | IN22810 | Indiana | 2016-06-02 | TS | 2 | 2.1 | No evidence of all SDD's documented in Clarity–technical solution access in JIRA | LI
IN CY15 Hoosier Lotto/New Game | IN22810 | Indiana | 2016-06-02 | TS | 2 | 2.1 | • No evidence of peer review for the documents listed below. o SDD ESTE, IPS/ESIPS, ESOLPM, Terminal, ESRS, and ESMM o RN ESTE, IPS/ESIPS, ESOLPM, Terminal, ESRS, and ESMM | LI
IN CY15 Hoosier Lotto/New Game | IN22810 | Indiana | 2016-06-02 | VER | 2 | 2.2 | No evidence of QA test plan peer review | NI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | PP | SG1 | 2.3 | No evidence of SPP fully completed. Unable to verify Configuration Management Lead assignment, System Architectural Design (6.1), Software Coding (6.2.1), System Testing (6.4), Software Operational Support Environment (7.4). | LI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | IPM | SG1 | 1.1 | OBSERVATION: No evidence of the approved Tailoring Request for using SharePoint as a project repository. | OBV
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | IPM | SG1 | 1.7 | OBSERVATION: No evidence of Lesson Learned. The project went live on 26-Jun. It will be verified during final CAPA. | OBV
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | PMC | SG1 | 1.7 | Unable to verify Weekly Staff Meetings since mid of May; however the project went live on 26-Jun. | LI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | PMC | SG1 | 1.7 | Unable to verify Development/Integration Phase Milestone Review. | LI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | PMC | SG1 | 1.6 | No evidence of Go Live Meeting; however the project went live on 26-Jun. | NI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | PMC | SG1 | 3.1 | No evidence of Change Request #1 closed out by changing the status to 'Closed' as the project went live. (CM 3.1) | LI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | RD | SG1 | 1.2 | No evidence of SRS (BRS) created as per process. The teams follows BRS document for requirements. It was not approved by RD Process Owner. | PI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | TS | SG1 | 2.1 | Unable to verify ES BIS in HLD (functional document for all disciplines). | PI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | TS | SG1 | 2.1 | No evidence of Critical Code data included for ESTE. | PI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | TS | SG1 | 2.1 | Lack of Critical Computer Resources identified for HLD ESTE and ES BIS. | NI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | PI | SG1 | 1.1 | No evidence of Integration Log. | NI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | PI | SG1 | 3.4 | No evidence of Installation Plan. | NI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | VER | SG1 | 2.1 | No evidence of peer review activities monitored for completion during weekly mtgs. | NI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | VER | SG1 | 2.1 | No evidence of any Peer Review documented in Clarity, PRMS nor SharePoint for the following work products: o SRS (FRD) o SDDs (HLD) ESTE and ES BIS o Installation Plan | LI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | VAL | SG1 | 2.1 | No evidence of Summary Site Test and CAT Report. | NI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | MA | SG1 | 1.1 | Unable to verify all project metrics reviewed during project status mtgs. | PI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | CM | SG1 | 1.3 | No evidence of CM Development, Integration, SQA, CAT and Production baselines for defined milestones. There is no SBI nor Phase Milestone Review Meetings documented. | NI
LUX CY16 Bulk Wagering | LUX23418 | Luxemburg | 2016-07-28 | CM | SG1 | 3.1 | Unable to verify the project reports the status of Configuration Items during weekly meetings. | NI
MEX CY15 Maintenance Batch A | MEX21455 | Mexico | 2016-07-07 | PI | 1 | 1.1 | No evidence of Integration Log for Release 2 | NI
MEX CY15 Maintenance Batch A | MEX21455 | Mexico | 2016-07-07 | CM | 1 | 1.3 | • No evidence of CAT Product Release Request for all Releases 1 • No evidence of Production Product Release Request for Releases 2 | LI
MEX CY15 Maintenance Batch A | MEX21455 | Mexico | 2016-07-07 | PMC | 1 | 1.7 | No evidence project fully completed milestone reviews for Release 1 and Release 2 | LI
MEX CY15 Maintenance Batch A | MEX21455 | Mexico | 2016-07-07 | PP | 2 | 2.7 | No evidence of SPP approved | LI
MEX CY15 Maintenance Batch A | MEX21455 | Mexico | 2016-07-07 | TS | 2 | 2.1 | • No evidence of approvals for SDD Host, IPS and ESRS - Release 1 • No evidence of approvals for SDDs Host, IPS Host, ESRS, B2B, ESBI and ESOLPM - Release 2 (R 2) • No evidence of approval for SDDs ESRS - Release 2.5 • No evidence of approvals for RNs ESTE/Host, IPS Host, ESRS, ESBI and ES OLPM - R 2 | LI
MEX CY15 Maintenance Batch A | MEX21455 | Mexico | 2016-07-07 | VER | 2 | 2.2 | • No evidence of QA Test Plan Peer Review for Release 1. • No evidence of SDDs ESRS, OLPM Peer Reviews for Release 1. • No evidence of Installation Plan Peer Review for Release 1 • No evidence of QA Test Procedure peer reviews for Release 2 | PI
MEX CY15 Maintenance Batch A | MEX21455 | Mexico | 2016-07-07 | VER | 2 | 2.3 | No evidence of RNs IPS Host, ESRS, ESBI and ESOLPM peer reviews completed in PRMS for Release 2. | PI
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | PP | SG1 | 1.1 | Late work product documented. - PSS approved by ADM, RL and Customer. | LI
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | PMC | SG1 | 1.7 | Late work product documented. - Customer approval to go to CAT. | LI
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | RSKM | SG1 | 1.1 | No risks logged for the project at all. | OBV
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | TS | SG1 | 2.1 | No evidence of SDDs GWARE Host and GWARE PC. - It 's not an issue. GWARE Host and GWARE PC not needed as no changes were necessary for those disciplines
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | TS | SG1 | 2.1 | Late work product documented. - Unable to verify SDD ETL approval. | LI
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | TS | SG1 | 2.1 | No RNs GWARE Host and GWARE PC. - It 's not an issue. GWARE Host and GWARE PC not needed as no changes were necessary for those disciplines
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | PI | SG1 | 1.1 | Integration Log is incomplete. The Log tab regarding Build and Deployment is not filled out. No Test Case Execution Results completed. | PI
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | PI | SG1 | 1.1 | Unable to verify CAT and Production Product Release Requests. (CM 3.1) | NI
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | PI | SG1 | 3.4 | Late work product documented. - No evidence of Installation Procedure. | NI
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | VER | SG1 | 2.1 | Late work product documented. - No evidence of the Test Summary approved by PM. (VAL 2.1) | LI
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | VER | SG1 | 2.2 | No evidence of peer reviews for the following work products: - SDDs ETL peer review - SDDs GWARE Host and GWARE PC peer review - It 's not an issue. GWARE Host and GWARE PC not needed as no changes were necessary for those disciplines - RNs GWARE Host and GWARE PC peer review - Late Peer Review Work Product documented. - Install Peer Review | LI
NC CY1602 AON & Promo Batch | NC23629 | North Carolina | 2016-07-28 | VAL | SG1 | 2.1 | Late work product documented. - No evidence of Summary Site Test and CAT Report. | LI
NE CY1601 Lake Ogalla | NE22679 | Nebraska | 2016-07-25 | CM | SG1 | 3.1 | No evidence of CM Production Baseline. | LI
NE CY1601 Lake Ogalla | NE22679 | Nebraska | 2016-07-25 | PI | SG1 | 1.1 | Integration Log is incomplete. | LI
NE CY1601 Lake Ogalla | NE22679 | Nebraska | 2016-07-25 | VAL | SG1 | 2.1 | No evidence of Final QA Summary Report and Final Site/CAT report. | LI
NE CY1601 Lake Ogalla | NE22679 | Nebraska | 2016-07-25 | VER | SG1 | 2.1 | No evidence of QA Test Procedure Peer Review | LI
NE CY1601 Lake Ogalla | NE22679 | Nebraska | 2016-07-25 | SAM | SG1 | 1.1 | Project used suppliers to fulfill hardware requirements for the project. | Obv